## Support
Task | Owner | ETA | Comments
Create a SR or talk to Dipen to get all our support team members access to SNOW modules including Enhancement | Chirag | 12th Aug | Individual users have created tickets, provided ticket numbers to Ravinder / Dipen for approval
Incident QE1 to PE1 testing | Shripad | 12th Aug | Tested and working on local. Check connectivity from PROD to QA and make minor adjustments.
MOIC: SKU Change issue | Nakul | 12th Aug | Data issue, nothing we need to do
MOIC: Dale email revert with action | Safee | 12th Aug
DMX: Search issue - raised by Walter few days back | SAP | 13th Aug | Something with SAP API
MOIC: Issue in PROD related to Orders, SKUs missing in MOIC | Safee / Sweta / Nakul | 13th Aug
DMX: INC1500671 (tracked as ENHC0016580) | Chirag / Barry | 26th Aug | Discussion needed internally for workflow. Try to see if we can have any work around, Shripad looking at what checks are present at the moment Conclusion: Short term solution to go into DMX PROD tomorrow. For long term solution, create a new ENH and implement accordingly
DMX: INC1511944 | Chirag / Shripad | 26th Aug | Checking if there is any API which can be triggered to insert the new company codes behind the scenes without the company codes added to SAP PE1. Call with Karthik at 7 pm to discuss solution possibilities Prior to the call, let us check background in specs for phase 2, etc. We will push it to PROD along with INC1500671
PMDB: Discrepancy between sizescalemaster and sizescalemoa | Sweta | 31st Aug | Think long term and permanent solution Checking Found more discrepancies between sizescalemaster and sizescalemoa How are sizes being sent from ECV to PMDB? Some issue probable with our PMDB code (size scale related) Tariq / Mike email on size 0 not coming into PMDB - as per our analysis, size 0 has always been ignored in the code. Revert with details on the email thread
JE Processing: Power shell script | Nakul / Safee | 25th Aug | Lookup table read and get the correct Period - script 1 Loop through the folders to check for the file in Input folder - script 2 Merge N and S scripts and testing on local Path with filename
Reply to Tarun on Site ID | Vatsal | 20th Aug | We don’t need to do anything for Site
MOIC: Dale email reply | Safee / Nakul | 25th Aug
PMDB: On QA run query to clean up Dbinput_events and archive data | Sweta | 31st Aug | Write query for QA to clean up Dbinput_events and dump the data older then 3 months into an archive table
PMDB: RPAS interface | Sweta | 1st Sept | Jobs are present in both; QA and PROD CTASK to be created in CR given by Mike to enable jobs in both; QA and PROD Frequency to be confirmed Delta changed from one day to 3 days (in both; QA and PROD)
Gift Voucher - brief document | Nakul | 27th Aug
MOIC: Delete script for Orders as per Dale's list. Create emergency CR and CTASK for Rama to execute the script | Safee / Nakul | 25th Aug
Send power shell script to Dan & if needed walk him through the script | Safee / Nakul | 25th Aug
KT to JE Processing team for scripts | Safee / Nakul / JE Team | 31st Aug
DMX: Prepare a brief document for new users, etc. | Shripad / Chirag | 31st Aug
MOIC: Think about statistics / reports | Vatsal | 16th Sept | Vatsal to finalize and send to Karthik
MOIC: Check if incoming orders from Joor exist in Archive and filter them from active orders | Safee / Nakul | 1st Sept | Implementation and Testing - for rollout to QA
DMX: Create ENH for long term solution for dropdown CSV upload | Vatsal | 1st Sept | On HOLD
Prepare details of all dropdowns sync from SAP to DMX for sharing with Karthik | Shripad | 1st Sept
MOIC: populate QA with latest orders | Safee / Nakul | 1st Sept
PMDB sizescale issue solve and deploy on PROD With this deploy, the earlier added 5 new attributes will also go to PROD | Sweta | 15th Sept | We have CR. We will create CTASK and Release Note. Deploy to Production happens tomorrow.
MOIC: Deploy on PROD (ignoring same orders) | Safee / Nakul | 7th Sept | Waiting on CR for production push
DMX: Document for SOP | Chirag / Shripad | 13th Sept | In internal review with Vatsal
PMDB->RPAS integration No change to LPPRICES and or ProductRenames (Code: Middleware Batch Extract) | Vatsal / Sweta | 8th Sept | Create CTASKs QA TiDAL (Frequency, days to run, etc.) PROD TiDAL (Frequency, days to run, etc.) PROD old jobs for disabling in QA and PROD (Nightly Outbound)
MOIC: Dale email and incident INC1529994 | Nakul / Safee | 6th Sept
PMDB - Revert to Tariq's email with details | Sweta | 3rd Sept
PLM Viewer issue (incident) | Safee / Chirag | 6th Sept | Latest code on QA, test and update the incident in SNOW
PLM Viewer - CR creation and PROD deploy | Chirag | 9th Sept | 1:30 pm IST prod deployment
MOIC - new Incident from Dale INC1534488 | Safee / Nakul | 8th Sept | Analysis and revert to Dale in email and through Incident
DMX / RPA: Incident INC1533946 - coordinate with Teenu | Chirag / Teenu | 8th Sept
PMDB -> RPAS QA CTASKs executed, job enabled from 15th @ 5:30 pm EST | Sweta | 15th Sept | Follow up and update Tariq / Mike CTASKs for QA jobs completed by support team Testing on QA is failing, file not getting generated (issue with garbage collection, need to increase memory)
MOIC: 2 Incidents in SNOW | Safee / Nakul | 13th Sept | UPC code not in sync between MOIC and CORA Update both incidents based on analysis and findings
DMX: 2 Enhancements in SNOW | Chirag | 15th Sept | Once completed, we will create a CR to push these into Production
PMDB: Code Table service - multiple issues | Sweta |  | Keep it on HOLD, we will not bring it up from our end Continue fixing this in background
PMDB: ENHC0016700 (new attributes) | Sweta | 16th Sept | Add PM SEGMENTATION SILHOUETTE in PMDB Code Table. This is in works.
MOIC: INC1538282 | Safee / Nakul | 14th Sept
MOIC: SKU Change issue - fix put in PROD | Safee | 15th Sept | SKU change impacting more then 1 account
MOIC: UPC codes in MOIC | Safee | 16th Sept
DMX: Patch applying this Saturday, we have to be available for support and testing after patch is applied | Chirag | 18th Sept | As discussed on call with Karthik
PMDB -> RPAS PROD CTASKs to be updated | Sweta | 17th Sept | As discussed
DMX: CR deployment | Chirag | 17th Sept | Update enhancement IDs after prod deployment
MOIC: ENHC0016740 | Safee | 17th Sept
MOIC: Fill integrations sheet sent by Karthik | Safee / Vatsal / Nakul | 21st Sept | Internally discuss
PMDB->RPAS, jobs to be enabled from 23rd instead of 24th. | Sweta | 21st Sept | CTASK to be updated
JAVA work: Nakul for 3 months | Vatsal | 21st Sept | Follow up with Abhijeet on SOW submission
SysDocument checklist based on template | Chirag | 22nd Sept | Finalize the template & check list
MOIC: Analysis of SKUs & UPCs in MOIC & PMDB | Safee / Sweta / Nakul | 21st Sept
MOIC: Investigation on customer (active / inactive) | Safee / Nakul | 22nd Sept | Check what is happening and fix the association of Orders to active customers
MOIC: Analysis for Orders aggregation | Safee / Nakul | 22nd Sept | Before filling finalbuy outbound staging table, check for aggregating quantity
MOIC: Integration sheet - expand with more details | Vatsal / Safee / Nakul |  | No further action from our end. Dale is the Owner.
MOIC front end knowledge and details | Shirpad | 23rd Sept
PMDB->RPAS: TiDAL jobs in PROD | Sweta | 22nd Sept | LPPrice job did not run on PROD yesterday
PMDB->RPAS | Sweta | 24th Sept | Check the files on PROD server Place the PRODMAST and LPPRICE files on egnyte and share the link with Surendar Create CTASK for pushing the PRODMAST changes to PROD for Monday
MOIC: 2 enhancements | Safee / Nakul | 27th Sept | Monday on QA CR and CTASK date final - production push
MOIC: Access for Shripad on DEV and QA | Safee | 24th Sept | Raise request or send email to Kevin
KT and understanding other JAVA apps (CoachSmart, PMDB / etc.) | Shripad / Chirag | 6th Oct | Understanding CoachSmart code base - its in ReactJS Local setup running into some issues. For debug needs local setup Setup of CoachSmart done on local, tables of CoachSmart added to Oracle PMDB Database
PMDB->RPAS and PMDB->Automail and PMDB->GSM | Sweta | 29th Sept | Prepare integration details sheet (reference MOIC integration sheet)
DMX / CoachSmart Integrations | Shripad | 27th Sept | Prepare integration details sheet (reference MOIC integration sheet)
Fix SysDocument template | Vatsal | 24th Sept
MOIC: Time Lag in UPC Codes between PMDB and MOIC | Safee / Nakul | 28th Sept | MOIC staging to MOIC live timings Job timings properly and check the dependencies CTASK needed for increasing the frequency
PMDB->RPAS job fixes | Sweta | 27th Sept | CTASK created, pushing to PROD today at 2 pm Verify the job on PROD by triggering it
MOIC: Mail from Dale, updating customer not happening on QA | Nakul | 27th Sept | Check if its data related
PMDB->RPAS: Check with Chirag on middlewarebatch program for LPPRICE job | Sweta / Chirag | 28th Sept | For LPPRICE job Manually ran LPPRICE query on Production and generated the file for delta 17th to 23rd
PMDB: CTASK for pushing attribute "SEGMENTSILLHOUTE" in Production scheduled for 2 pm today | Sweta | 28th Sept | SEGMENTSILLHOUTE attribute to be added and pushed to Production
DMX: SSO authentication moving to Azure | Chirag / Shripad | 28th Sept | Test on DEV. This is only for testing purpose and will not be pushed to QA / PROD until sometime in 2022.
PMDB->RPAS: Generate new LPPRICE file | Chirag / Sweta | 29th Sept
PMDB->RPAS: Dig into ProductRename job for understanding | Sweta / Chirag | 11th Oct | Latest codebase, understanding, etc. Sync up TPR DEV with our local environments - if required
CoachSmart: IE to Chrome, uses VBscript which is compatible with IE and Edge | Chirag |  | Talk to Devakar for replacing IE to Edge On HOLD
Check PMDB integrations sheet | Vatsal | 1st Oct
PMDB: Mike's email on SKU issue | Sweta | 1st Oct | Issue sent in email: SKU not reaching JOOR
MOIC: QA environment Orders & Quantity issue (email from Dale) | Safee / Nakul | 1st Oct | Reply to Dale with explanation
PMDB->RPAS (attribute name issue) | Sweta
MOIC: Monitoring UPC codes from A360 to MOIC | Safee / Sweta / Nakul | 1st Oct | TiDAL corrections done on 4th Oct. Continue monitoring
Check list template filled up | Team | 5th Oct | Fill up the server details for all applications
PMDB - Segment Silhoute | Sweta |  | Call scheduled
DMX: SSO change brief document | Chirag | 6th Oct | Send to Karthik, he will send to business
DMX: SSO change move to QA and then to PROD plan with Kevin | Chirag | 7th Oct | Keep Karthik also in email loop
MOIC: Incident from Kasey | Safee | 8th Oct | Need to discuss this with Dale for cleaning possibility
PMDB to RPAS: Incident INC1564545 | Sweta | 8th Oct | Checked and found that PMDB has sent these to RPAS in the file.
MOIC: New incident from Dale on Orders mismatch | Safee | 11th Oct
MOIC: Delete customer script as per Dale's email | Safee | 13th Oct
MOIC: Enhancement for considering Season in MOQ | Safee | 14th Oct
PMDB: Alerts from Server and tracking | Sweta / Chirag |  | 1. Check if we received the low memory alert. If not, follow up with Support team to confirm that we receive the email alert. 2. How to check automatically that our PMDB services are up? 2.1 Springboot->Actuator for endpoints checking, memory check (exploring this) 3. Maximum size set in Tomcat? (Add CTASK in the CR) 4. Everyday manual checking of PROD services to be up.
MOIC: Watch the SKUs for UPC Code, check the jobs and counts, TiDAL jobs in QA | Safee | 18th Oct
DMX: Proactive monitoring, similar to PMDB app | Chirag | 27th Oct | Service request for URL monitoring for DMX
MOIC: Proactive monitoring, similar to PMDB app | Safee / Nakul
MOIC: Dale email | Safee | 19th Oct
MOIC: TiDAL jobs on QA | Safee | 19th Oct
DMX: Incident from Walter: INC1578211. Created enhancement ENHC0016893 for code change. | Chirag / Shripad | 19th Oct | For code change, create enhancement ID and resolve the incident with that enhancement ID
Connect with Unix Team and discuss on all different notifications that they currently have at server / app level. (for all our apps) | Chirag / Team |  | Need to find out what all notifications are set at server level already which can help with proactive alerts. Add our support email to those alerts. Follow up with Tools team Services URL monitoring - PMDB services, CoachSmart, PLMViewer, PMDBViewer services
Create a support roaster and fill it up | Vatsal | 21st Oct | Vatsal to create the template, team to fill up
Create a template for server / DB / access details for all apps | Vatsal | 21st Oct | Need to see if passwords can be encrypted / de-crypted or the excel sheet can be password protected.
MOIC: Dale email | Safee | 21st Oct
MOIC: Enhancement created for new users addition | Safee | 21st Oct
MOIC: Connect with Vikas / Sandhya for JOOR API call | Safee |  | Some issue with ETL job. Sandhya following up with ETL
Server Move: Prepare list of dependencies, things that is relevant to PMDB application for server move activity. | Nakul / Sweta / Chirag | 28th Oct | Draft version of consolidated list prepared. Send an update to Ravinder / Biswajit - draft list sent.
MOIC: Revert to Karthik's email with details | Safee | 28th Oct | Gather all the details for Milan week
DMX: CI / CD discussion going on with Infosec team (Sumlata) | Chirag / Shripad |  | Which job is being used? We need Jenkins dashboard to check the job name
On Call Support Roaster - Update | Team
Server Move: Send template of execution plan | Vatsal |  | To team
MOIC: MOQ change on QA is signed off | Safee |  | CTASK created by Dale but is not approved
MOIC: Co-ordinate with ESB / ETL for jobs frequency increase (as discussed on call yesterday with Karthik) | Safee | 3rd Nov | UPC Code jobs frequency increase on QA Orders jobs frequency increase on QA
MOIC: Add the status column in Overview report - go ahead from Chris in email | Safee
Server move: Execution plan v 1.0 | Chirag | 3rd Nov
DMX: Fix deployed to Production | Chirag / Shripad | 3rd Nov
Coachsmart: Credentials sent for URL monitoring | Chirag | 3rd Nov