## Prod
MOIC tech checklist
S.No | Items | Owner | Target date | Status | Comments
Pre-build activities
1 | Prod APP server build | Kamlesh/Atanu | 2021-02-22 | Done | Vatsal & team should confirm access
2 | Prod DB server build | Mohan/Rama | 2021-02-22 | Done
3 | Firewall rules for Ingress/Egress | Kamlesh/Mohan/Karthik | 2021-02-26 | Done | Vatsal and team should check connnectivity
4 | Firewall rules for App & DB server | Karthik | 2021-02-26 | Done | Vatsal and team should check connnectivity
5 | Install MFT & TIDAL agents on App server | Atanu | 2021-03-12
6 | Request for APP server access | Vatsal | 2021-02-26 | Done | Vatsal and team should check connnectivity
7 | Enable sudo access for Prod app server | Kamlesh/Atanu | 2021-02-26 | Done | Vatsal & team should confirm access
8 | Create S3 bucket for Prod | Mohan | 2021-03-19 | Need an update
9 | Enable MFT access to S3 bucket | Mohan/MFT team | 2021-03-19 | Need an update
10 | SSO setup for Prod App server | Vatsal/Kevin/Atanu | 2021-03-19 | In Progress

## QA
MOIC tech checklist
S.No | Items | Owner | Target date | Status | Comments
Pre-build activities
1 | QA APP server build | Kamlesh/Atanu |  | Ready | Vatsal & team should confirm access
2 | QA DB server build | Mohan/Rama | 2021-03-05 | Ready
3 | Firewall rules for Ingress/Egress | Mohan | 2021-03-05 | Ready | Vatsal & team should confirm access
4 | Firewall rules for App & DB server | Karthik | 2021-03-05 | Ready | Maynot be required as it is the same host as the Dev server
5 | Install MFT & TIDAL agents on App server | Atanu | 2021-03-10
6 | Enable sudo access for QA app server | Kamlesh/Atanu | 2021-03-05 | Ready | Vatsal & team should confirm access
7 | SSO setup for QA App server | Vatsal/Kevin/Atanu | 2021-03-12 | In Progress