## Execution Plan
Project Name: PMDB ReVamp Client Name: Tapestry Execution Plan |  |  |  |  | November | [14 empty] | December | [30 empty] | January | [29 empty] | February | [27 empty] | March
Project Name: MOIC System Development Client Name: Tapestry Execution Plan |  |  |  |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5
Phase | Tasks | Status | % Completion | Owner
Requirements Consolidation Phase | SOW signoff and PO |  | 100 | Tapestry / CD | bar: November 16 to November 17
| Team Finalization (Offshore) |  | 100 | CD | bar: November 19 to November 20; November 23 to November 27; November 30 to December 4
| Project Kick off |  | 100 | Tapestry/ CD | bar: November 24
| VDI access to Tapestry environments |  | 100 | Tapestry | bar: November 26 to November 27; November 30 to December 4; December 7 to December 11; December 14 to December 18; December 21 to December 25; December 28 to January 1; January 4 to January 8; January 11 to January 13; January 15
| Software Requirements Specifications (SRS) |  | 100 | CD | bar: November 30 to December 4; December 7 to December 11
| Software Requirements Specifications (SRS) - signoff |  | 100 | Tapestry | bar: December 14 to December 15
| Design Document creation |  | 100 | CD | bar: December 7 to December 11; December 14 to December 18; December 21 to December 25
| Design Document - signoff |  | 80 | Tapestry | bar: December 14 to December 15; December 21 to December 24
| Integrations - Conclusion with middleware team |  | 90 | Tapestry/ CD | bar: December 3 to December 4; December 10 to December 11; December 14 to December 17; December 21 to December 24; December 29 to December 30
| Integrations - Conclusion with JOOR team |  | 100 | Tapestry/ CD | bar: November 30 to December 2; December 7 to December 9; December 14 to December 15; December 21 to December 24
| Integrations - Conclusion with PMDB team |  | 90 | Tapestry/ CD | bar: December 10 to December 11; December 14 to December 18; December 21 to December 24; December 29 to December 30
| Integrations - Conclusion with S4 team |  | 100 | Tapestry/ CD | bar: December 7 to December 9; December 14 to December 18; December 21 to December 24; December 28 to January 1
| Screens Design (non functional) |  | 100 | CD | bar: November 30 to December 4; December 7 to December 11; December 14 to December 16
Development Phase | MOIC DB schema finalization |  | 95 | CD | bar: December 14 to December 17
| MOIC DB scripting |  | 100 | CD | bar: December 15 to December 17
| MOIC Project Structure (Framework & Folders) finalization |  | 100 | CD | bar: December 10 to December 11; December 14 to December 18
| MOIC - Communication layer for integrations Define Inbound and Outbound services (for Joor integration) |  | 100 | CD | bar: December 21 to December 25; December 28 to January 1; January 4 to January 8; January 11 to January 15; January 18 to January 20
| MOIC - Overview (Internal APIs + UI integration) |  | 80 | CD | bar: December 21 to December 25; December 28 to December 31; January 4 to January 8; January 18 to January 20; January 25 to January 28; February 2 to February 4
| MOIC - MOQ (Internal APIs + UI integration) |  | 100 | CD | bar: December 28 to January 1; January 4 to January 7; January 11 to January 13
| MOIC - SKU Change (Internal APIs + UI integration) |  | 100 | CD | bar: December 30 to January 1; January 4 to January 5; January 18 to January 20; January 25 to January 26
| MOIC - UPC Validation (Internal APIs + UI integration) |  | 10 | CD | bar: January 11 to January 12; January 25 to January 28; February 4 to February 6
| MOIC - S4 Upload File (Internal APIs + UI integration) |  | 75 | CD | bar: January 25 to January 28
| MOIC - Config (Internal APIs + UI integration) |  | 100 | CD | bar: December 29 to December 31; January 4 to January 8; January 18 to January 22
| MOIC Reports - Excel exporting from screens |  | 90 | CD | bar: December 21 to December 25; December 28 to January 1; January 4 to January 8; February 4 to February 6
| MOIC - Excel importing from UI (module with configurable import) |  | 90 | CD | bar: December 28 to January 1; January 4 to January 8; January 11 to January 15; February 4 to February 6
QA Testing | System Test Plan Ready |  | 100 | CD | bar: December 21 to December 24; December 28 to December 31; January 4 to January 8
| Testing in non-integrated enviornment (sampling basis) |  | 25 | CD | bar: December 28 to January 1; January 11 to January 15; January 18 to January 22; January 25 to January 29; February 2 to February 6; February 9 to February 13
| Testing PMDB integration |  |  | CD | bar: January 25 to January 26; February 2 to February 6; February 9 to February 13
| Testing - JOOR integration |  |  | CD | bar: February 3 to February 5; February 9 to February 13
| Testing - S4 integration |  | 10 | CD | bar: February 6; February 9 to February 10
| Integrated Testing with all connections |  |  | Tapestry / CD | bar: February 2 to February 6; February 9 to February 13
UAT Release to Tapestry | User Acceptance Testing |  |  | Tapestry | bar: February 16 to February 20
| Bug fixing and UAT deployment |  |  | CD | bar: February 17 to February 21
Interim Release 1 | Interim Release (releases pushed to DEV / QA environments) for interim feedback |  |  | CD | bar: February 2 to February 3
Final Release to QA | Final Release to QA on QA environment (For integrated testing) |  |  | CD | bar: February 12 to February 13
Final Release to UAT | Final Release on UAT environment |  |  | CD | bar: February 12 to February 13
Note on D3: ORANGE = WIP GREEN = Dev Complete